NHM — SOLO IMPLEMENTATION & EXECUTION PLAN

Executable one-developer build plan derived from the locked v2.2 specification

Version 1.0  |  27 September 2026  |  Status: EXECUTION BASELINE

| Field | Decision |
| --- | --- |
| Authoritative technical source | NHM_ML_Revised_Locked_Specification_v2.2.docx |
| Supporting sources | Original NHM ML Development Plan; Detailed ML Work Division; Solo Planner master prompt |
| Execution owner | One developer; independent verification is a review role, not a second owner |
| Planning horizon | 16-week Full path; 12-week Robust-Reduced path; Emergency path preserves scientific core |
| Clinical boundary | Research prototype only; no diagnosis, treatment recommendation, clinical readiness, or patient-safety claim |
| Core rule | Rigor before breadth; contracts before consumers; validation before optimization; centralized validity before distributed complexity. |

This plan does not redesign v2.2. Any change to a frozen scientific decision requires a new version, impact analysis, and regeneration of all invalidated evidence.

# 1. Executive Solo-Implementation Strategy

The solo plan converts the old P1/P2/P3 parallel ownership into one dependency-driven critical path while preserving fixture-based early progress. The developer works in coherent batches and only crosses subsystem boundaries at explicit interface freezes. The first usable vertical slice is built on Day 1 with fixtures; real-data evidence replaces fixtures gate-by-gate.

| Principle | Operational rule |
| --- | --- |
| Single owner, multiple roles | The same developer implements data/ECG, multimodal quality/context, FL/privacy, deployment/API and evidence; role switching occurs only at batch boundaries. |
| Hardware-first risk, software-not-blocked | Bench and document all VERIFICATION REQUIRED hardware items immediately, but continue software with canonical fixtures until hardware fields are frozen. |
| Vertical slices | Slice 0 fixture→contract→mock state→API; Slice 1 real ECG→MODEL_V1→evaluation; Slice 2 multimodal quality→episode manager→controlled robustness; Slice 3 frozen model→FedAvg→evidence; Final slice wearable→gateway→API→dashboard. |
| Freeze before comparison | Target, mapping, lead rule, split, preprocessing, model, calibration and FL/client manifests are frozen before any held-out/comparative result is interpreted. |
| Evidence generated, not reconstructed | Every experiment emits config, run manifest, predictions, metrics, plots and hashes during execution. |

## Toolchain engineering decision

Use Python 3.11.x as the project baseline because current Flower requires Python 3.11+ and v2.2 already depends on a PyTorch/Flower workflow. Resolve exact package versions on the implementation host once, commit the lockfile, and never silently upgrade inside the evidence-producing release branch. Use PyTorch for MODEL_V1, WFDB for PhysioNet-format data, SciPy/NumPy/pandas/scikit-learn for processing/baselines, Captum for the locked Integrated Gradients method, Flower for simulation/SecAgg+, FastAPI/Pydantic for the typed local API, and pytest for tests. Exact resolved versions are evidence, not hard-coded here without the implementation host.

Current Flower stable documentation reports Python >=3.11 and stable Flower 1.39.0; use flwr[simulation] for the simulation runtime. Re-verify on Day 1 and record the resolved version in ENVIRONMENT.md.

PyTorch installation is host-specific; resolve it using the official PyTorch install path, then lock the exact wheel/version before MODEL_V1 evidence runs.

# 2. Document Reconciliation and Locked Decisions

| Topic | Earlier source direction | Authoritative v2.2 decision | Solo execution consequence |
| --- | --- | --- | --- |
| Core dataset | PTB-XL primary; MIT-BIH external | MIT-BIH development/internal; INCART external; PTB-XL removed | Do not build PTB-XL loaders on critical path. |
| Target | Broad abnormal rhythm / health-risk wording | AAMI_SVF_WINDOW_V1: 10-s single-lead window, S/V/F-containing vs N-only | All labels/tests/configs named after the locked target. |
| Multimodal ML | Learned late-fusion classifier | No learned SVF fusion; deterministic ECG+PPG+SpO2+HR quality/context and operational robustness experiment | P2-era work becomes quality/sync/episode research, not a second classifier. |
| Channels | Single lead not fully locked | MIT-BIH MLII; INCART Lead II; no performance fallback | Lead selector is deterministic and tested before splitting. |
| Preprocessing | General filtering/resampling | Stateful causal resampling/filtering; GAP_POLICY_V1 | Future-append and chunk-equivalence tests block modeling. |
| Baseline | Majority wording ambiguous | Majority class from training prevalence only | Freeze baseline predictor before held-out evaluation. |
| Alert logic | Window outputs only | ALERT_POLICY_V1 K=2/M=2/cooldown=30 s | All false-alert metrics are episode-level. |
| FL clients | Patient groups / simulated clients | 8 synthetic whole-training-patient research sites | Never call sites hospitals; save patients/site. |
| Privacy | Secure aggregation + optional DP | SecAgg+ mandatory experiment; DP extension-only | Plain aggregation must pass before privacy work. |
| Deployment | ESP32/edge ambiguity | Gateway inference mandatory; ESP32 acquisition; MCU inference optional | Do not spend critical-path time on TFLite Micro. |
| Explainability | Saliency/IG options | Integrated Gradients only, zero normalized baseline, 64 Gauss-Legendre steps | Captum-based deterministic report after MODEL_V1/test freeze. |

Authority rule: where earlier documents conflict with v2.2, v2.2 wins. Earlier documents remain useful only for intent, rationale and historical workflow.

# 3. Requirement-to-Implementation Coverage Matrix

| ID | Locked requirement | Task(s) | Validation | Gate | Evidence |
| --- | --- | --- | --- | --- | --- |
| R01 | AAMI_SVF_WINDOW_V1 + AAMI_SVF_MAP_V1 | T008,T013 | LABEL_SCHEMA_V1 + mapper tests | G4 | symbol census + label test report |
| R02 | 10 s window / 5 s stride | T013 | synthetic exact-boundary test | G6 | window_tests.xml |
| R03 | MIT-BIH MLII / INCART Lead II | T006,T007 | header-name selection + pre-split exclusions | G3 | lead_policy_audit.json |
| R04 | Patient-disjoint split + 201/202 grouping | T009,T010 | set disjointness + override assertion | G5 | split_audit.json |
| R05 | Causal resampling/filtering | T011,T012 | future-append + chunk-equivalence + impulse | G6 | resampler_causality.json |
| R06 | Short gaps <=100 ms causal ZOH; >100 ms break/reset | T012 | synthetic two-future gap tests | G6 | gap_tests.json |
| R07 | Majority baseline from train prevalence only | T014 | assert class chosen before held-out load | G7 | baseline_report |
| R08 | MODEL_V1 architecture/training contract | T015,T016 | config + checkpoint/test-vector reproducibility | G8 | MODEL_V1 package |
| R09 | Dedicated calibration + frozen threshold | T017 | partition provenance assertion | G10 | CAL_V1.json |
| R10 | Internal patient-cluster bootstrap | T018 | patient resample→pooled recompute | G10 | internal_test report |
| R11 | NSTDB robustness | T019 | predeclared SNR/noise protocol | post-G10 | noise report |
| R12 | INCART one locked external run | T020 | checkpoint/map/preprocess hash gate | post-G10 | external report |
| R13 | PPG/SpO2/HR context, no learned arrhythmia fusion | T021,T022 | BIDMC alignment/quality + deterministic state tests | G9 | BIDMC + fusion reports |
| R14 | ALERT_POLICY_V1 K2/M2/30s | T022 | scripted state-machine sequences | G9 | episode_tests.json |
| R15 | Controlled quality-aware experiment | T023 | paired clean/degraded streams with frozen seeds | G9 | quality_aware_alert_report |
| R16 | 8 simulated whole-patient FL sites | T025 | client manifest disjointness | G11 | client_audit.json |
| R17 | FedAvg 50 rounds / 1 local epoch / all clients | T025 | config lock + round log | G11 | fl_iid report |
| R18 | Non-IID label/quantity/feature conditions | T026 | manifest statistics + matched budgets | G12 | fl_non_iid report |
| R19 | FedProx matched; mu tune label-skew only | T027 | mu=0 equivalence + frozen mu | G13 | fedprox report |
| R20 | SecAgg+ narrow privacy claim | T028 | server-visibility instrumentation + aggregate correctness | G14 | privacy report |
| R21 | Gateway mandatory deployment | T029 | 1000-window benchmark + accuracy delta | G15 | edge report |
| R22 | WEARABLE_V1 domain validation only | T004,T030 | canonical ingest + activity/sync/quality evidence | G16 | wearable report |
| R23 | Integrated Gradients V1 | T031 | fixed baseline/steps/method/case rule | G17 | IG case report |
| R24 | Versioned API + safe semantics | T032 | schema/error/status contract tests | G18 | OpenAPI + API tests |
| R25 | Dashboard state wording | T033 | enum→UI mapping tests | G19 | screens/replay evidence |
| R26 | Run manifests, hashes, reproducibility | T001,T002,T035,T036 | clean env + registry audit | G20,G22 | repro + release manifests |
| R27 | G0–G22 blocking gates | all | gate checklist + artifact presence | G0–G22 | gate_status.json |
| R28 | Definition of Done | T036 | release checklist vs 12 DoD clauses | G22 | final_evidence_index |

Coverage rule: every new implementation finding is first checked against this matrix. If it changes a locked requirement, it is a specification change, not a local refactor.

# 4. Complete System Dependency Graph

SOURCE AUTHORITY / REPO / ENV
        |
        v
CONTRACTS + FIXTURES -----> MOCK API / STATE / DASHBOARD SLICE 0
        |
        +--> HARDWARE BENCH + PACKET/TIMESTAMP VERIFICATION ------------------+
        |                                                                    |
        v                                                                    v
DATASET MANIFESTS -> LEAD POLICY -> SYMBOL CENSUS/MAP -> PATIENT GROUPS -> SPLIT FREEZE
        |                                                                    |
        v                                                                    |
CAUSAL RESAMPLER/FILTER/GAPS -> WINDOWS/SYNC/QUALITY -> LEAKAGE GATE          |
        |                                |                                   |
        v                                +--> BIDMC PPG/SpO2/HR -> FUSION -> EPISODES
CLASSICAL BASELINES -> MODEL_V1 -> MODEL LOCK -> CALIBRATION -> INTERNAL TEST |
        |                          |                    |                    |
        |                          +--> NSTDB ----------+                    |
        |                          +--> INCART -------------------------------+
        |                                                                    |
        +--> CLIENT MANIFESTS -> TOY FL -> FEDAVG IID -> NON-IID -> FEDPROX -> SECAGG+
        |                                                                    |
        +--> GATEWAY EXPORT/BENCH -> API REAL MODEL -------------------------+
                                                                             v
WEARABLE_V1 -> CANONICAL INGEST -> QUALITY/CONTEXT -> MODEL -> EPISODE -> API -> DASHBOARD
                                                                             |
                                                                             v
                                                        CLEAN REPRO RUN -> RELEASE/EVIDENCE

| Dependency edge | Why blocking | Can fixture work proceed? |
| --- | --- | --- |
| Label/map/split -> model | Otherwise labels or patient identity can change after training. | No final model; yes runner/model-shape fixtures. |
| Causal preprocessing -> model | A look-ahead transform invalidates streaming evidence. | Yes model code on synthetic arrays, not evidence. |
| MODEL_V1 -> calibration/internal/external/FL final | Checkpoint hash defines downstream comparison subject. | Yes FL toy scaffold and API mocks. |
| Calibration -> episode thresholded evidence | Alert state requires frozen threshold. | Yes state machine using synthetic probability traces. |
| FedAvg correctness -> non-IID/FedProx/SecAgg+ | Advanced experiments cannot diagnose base aggregation bugs. | Yes partition builder and privacy config skeleton. |
| Hardware contract -> wearable evidence | Otherwise sensor meaning/timestamps are ambiguous. | Yes public-data and replay fixture work. |

# 5. Solo Critical Path

| ID | Critical-path batch | Effort window | Tasks | Gate | Reason |
| --- | --- | --- | --- | --- | --- |
| CP1 | Authority, repo, environment, contract skeleton | Days 1-2 | T001-T003 | G0/G1 skeleton | Any ambiguity here propagates everywhere. |
| CP2 | MIT-BIH/INCART manifests, map, grouping, split | Days 3-8 | T006-T010 | G2-G5 | No modeling until patient/target integrity is proven. |
| CP3 | Causal preprocessing/window/quality | Days 7-14 | T011-T013 | G6 | Future leakage would invalidate all later evidence. |
| CP4 | Baselines + MODEL_V1 lock | Weeks 3-5 | T014-T016 | G7-G8 | Unlocks calibration, FL real model, deployment. |
| CP5 | Calibration + internal test | Weeks 5-6 | T017-T018 | G10 | Defines frozen threshold and central evidence. |
| CP6 | FedAvg IID correctness | Weeks 7-8 | T024-T025 | G11 | Unlocks non-IID/FedProx/privacy conclusions. |
| CP7 | Non-IID + FedProx | Weeks 8-10 | T026-T027 | G12-G13 | Core FL research evidence. |
| CP8 | SecAgg+ + gateway + wearable integration | Weeks 10-13 | T028-T030 | G14-G16 | Highest integration/schedule risk; start no later than Week 10. |
| CP9 | API/dashboard/e2e + clean reproducibility | Weeks 13-15 | T032-T035 | G18-G21 | Converts research components to a demonstrable system. |
| CP10 | Final release evidence | Week 16 | T036 | G22 | No manual reconstruction allowed. |

Latest safe starts: hardware bench by Day 2; causal resampler by Day 8; MODEL_V1 training by Week 4; real FedAvg by Week 7; SecAgg+ by Week 10; wearable end-to-end by Week 12. Missing these triggers scope reduction, not compression of validation.

# 6. Context-Switch-Minimized Work Batches

| Batch | Focus | Included tasks | Intentionally postponed | Exit condition |
| --- | --- | --- | --- | --- |
| B0 | Bootstrap / authority | T001-T005 | Real ML, FL, UI polish | Fixture slice and contracts execute end-to-end. |
| B1 | Data integrity | T006-T010 | CNN/FL/benchmarking | G2-G5 pass; split and mapping frozen. |
| B2 | Signal processing | T011-T013 | Hyperparameter tuning | G6 causal/leakage tests pass. |
| B3 | Centralized ECG | T014-T020 | Privacy/UI cosmetics | MODEL_V1, calibration, internal/noise/external reports frozen. |
| B4 | Multimodal operational robustness | T021-T023 | Any learned fusion | G9 paired context experiment reproducible. |
| B5 | Federated research | T024-T027 | SecAgg+ until plain FL correct | G11-G13 pass. |
| B6 | Privacy + deployment | T028-T032 | MCU inference, fancy UI | G14-G18 pass. |
| B7 | Wearable + dashboard integration | T030,T033,T034 | New models/datasets | G16/G19/G21 pass. |
| B8 | Reproducibility + release | T035-T036 | New methodology | G20/G22 pass. |

# 7. Exact Repository / Module Creation Order

| Order | File/module | Purpose | First consumer | Validation | Freeze/consumer |
| --- | --- | --- | --- | --- | --- |
| 1 | pyproject.toml / .python-version / uv.lock or equivalent lock | Environment identity | shell/CI | pytest --version; import smoke | all |
| 2 | docs/SOURCE_AUTHORITY.md | Authority hierarchy + frozen sources | developer | manual + source hash list | all |
| 3 | contracts/sample_schema_v1.json | Canonical record schema | fixtures/loaders/API | JSON-schema/Pydantic fixture validation | T005+ |
| 4 | configs/base.yaml + config loader | Paths, IDs, seed policy | all runners | schema + hash determinism | all |
| 5 | experiments/registry.csv + training/run_manifest.py | Run provenance | all experiments | manifest completeness test | E01+ |
| 6 | tests/fixtures/* | Stable fixture data | preproc/fusion/API/FL toys | known-output tests | T005+ |
| 7 | contracts/HARDWARE_DATA_CONTRACT_V1.md | Hardware fields/timestamps | firmware/ingest | G1 review | wearable |
| 8 | datasets/mitdb.py / incart.py / nstdb.py / bidmc.py | Versioned loaders | standardization | dataset validation | data |
| 9 | datasets/labels.py | AAMI_SVF_MAP_V1 | window builder | allowlist census tests | model/external |
| 10 | datasets/grouping.py / manifests/splits/* | Patient groups/split | all supervised training | disjointness tests | all model evidence |
| 11 | preprocessing/resample.py / gaps.py / ecg.py | Causal preprocessing | window builder/runtime | future-append/chunk tests | MODEL_V1/runtime |
| 12 | preprocessing/ppg.py / sync.py / quality.py | Context quality | fusion/runtime | alignment/quality tests | RQ5/wearable |
| 13 | preprocessing/windowing.py | 10s/5s examples | training/runtime | boundary tests | MODEL_V1 |
| 14 | features/ecg.py / models/baselines.py | Classical baseline path | E01 | train-only fit tests | G7 |
| 15 | models/ecg_cnn.py / training/train_ecg.py | MODEL_V1 | E02+ | checkpoint determinism | G8 |
| 16 | evaluation/metrics.py / bootstrap.py / calibration.py | Locked evaluation math | E03-E06 | synthetic metric/cluster tests | G10+ |
| 17 | fusion/state_machine.py / episode_manager.py | Quality-aware state/episodes | API/dashboard/RQ5 | table-driven transitions | G9 |
| 18 | evaluation/context_alerts.py | Controlled RQ5 experiment | E08 | paired perturbation replay | G9 |
| 19 | federated/* | Toy→real FedAvg/FedProx | E09-E13 | analytical and μ=0 tests | G11-G13 |
| 20 | privacy/* | SecAgg+ experiment | E14 | aggregate/privacy-interface audit | G14 |
| 21 | deployment/* | Gateway export/replay/benchmark | E15/E16 | accuracy delta/resource tests | G15/G16 |
| 22 | api/* | Typed runtime service | dashboard/e2e | schema/error tests | G18 |
| 23 | dashboard/* | User/research UI | final demo | state wording tests | G19 |
| 24 | evaluation/explain.py / error_analysis.py | IG/error evidence | G17/viva | parameter/case-rule assertions | G17 |
| 25 | scripts/* / release/* | One-command execution/release | clean environment | smoke + artifact presence | G20-G22 |

# 8. Hardware Risk and Verification Plan

| Item | Earliest safe verification | Latest safe verification | Method/evidence | Software allowed before lock | Failure containment |
| --- | --- | --- | --- | --- | --- |
| ESP32 exact variant/ADC | Day 2 | Before G1 / Day 5 | board photo/model, ADC config, 10-min rate/jitter capture | fixture packet parser, public datasets | version HARDWARE_DATA_CONTRACT; do not guess mV conversion |
| AD8232 gain/filter/electrodes | Day 2 | Before first WEARABLE_V1 collection | schematic/board BOM + electrode placement photo/diagram | all public ECG work | record raw counts if calibration unresolved |
| MAX30102 registers/rate | Day 2 | Before BIDMC-to-hardware sync integration | firmware register dump + achieved Hz | BIDMC PPG work | freeze config hash; no medical SpO2 claim |
| SpO2 algorithm/provenance | Day 3 | Before G16 | library/algorithm/version note + valid flag behavior | PPG pulse/quality work | expose unavailable/invalid rather than fabricate |
| Packet schema/CRC/sequence | Day 2 | Before G1 | serial loopback/drop test | mock ingest/API | block wearable evidence if packet loss undetectable |
| Monotonic timestamp/jitter | Day 2 | Before G1 | timestamp diff histogram | public data work | fix timer path before real collection |
| Consent/ethics process | Week 1 | Before any volunteer collection | supervisor/institution approval record | all non-human work | use recorded synthetic/public streams only until cleared |

Hardware-independent track: all public-dataset data integrity, causal preprocessing, MODEL_V1, FL, API schema, dashboard state logic and replay harness can proceed with fixtures. Hardware-dependent track: actual raw ADC semantics, sensor configuration, packet integrity, synchronization and WEARABLE_V1 evidence cannot be declared complete until G1/G16 evidence exists.

# 9. Data + ECG Execution Plan

1. Acquire exact MIT-BIH/INCART/NSTDB versions via scripted download; create manifests with source URL, version, license, checksums and download date.

2. Validate raw records before transformation: parseability, channel names, sampling rates, annotations, finite values, durations, IDs, duplicate hashes.

3. Apply locked lead policy before splitting: MIT-BIH header channel exactly MLII; INCART header channel exactly II; persist exclusion list.

4. Generate raw annotation-symbol census for MIT-BIH and INCART; apply one pure AAMI_SVF_MAP_V1 allowlist; exclude unknown/paced/unlisted beats.

5. Resolve patient groups, including the MIT-BIH 201/202 same-patient override; create exactly one deterministic split manifest and freeze it.

6. Implement stateful causal rational/polyphase resampling, causal SOS filters and GAP_POLICY_V1. Block model work until future-append/chunk-equivalence/gap tests pass.

7. Create 10-second windows at 5-second stride only within partitions; right edge is prediction time; exclude UNUSABLE and ineligible-label windows.

8. Implement train-fit deterministic ECG features; fit scalers on train only. Train frozen-training-majority, logistic regression and random forest baselines.

9. Train MODEL_V1 exactly as v2.2 specifies; primary seed 20260927 selects release checkpoint; other seeds are robustness replicates only.

10. Freeze checkpoint/config/preprocess IDs and test vector. Fit temperature + F1 threshold only on calibration patients.

11. Run internal test once; patient-cluster bootstrap 2000 times. Then run NSTDB robustness and one locked INCART external evaluation without retuning.

# 10. PPG / SpO2 / Quality / Multimodal Plan

| Stage | Implementation | Test/evidence | Allowed conclusion |
| --- | --- | --- | --- |
| BIDMC loader | load ECG/PPG 125 Hz + 1 Hz numerics with timestamps/provenance | record and alignment audit | engineering synchronization only |
| PPG preprocessing | causal 0.5-8 Hz path, pulse detector, PR estimate, saturation/dropout checks | synthetic pulses + BIDMC provided pulse/HR numerics | algorithm agreement/descriptive error |
| SpO2 | pass through value + validity + algorithm/source version; no “ground truth” assumption | missing/out-of-range/provenance tests | context availability only |
| Quality | VALID/DEGRADED/UNUSABLE per modality; thresholds frozen on development resources | flatline/clipping/dropout/motion fixtures | quality-state behavior |
| Sync | align context to ECG window end using acquisition timestamps | known-offset shared-event fixture | timing correctness |
| Cross-modal consistency | retain hr_ecg and pr_ppg separately; warn on sustained disagreement | scripted disagreement >=10s | quality warning, not diagnosis |
| Fusion | deterministic state machine only | full state table unit tests | monitoring-state behavior |
| Episode manager | K=2 open; M=2 close; 30s cooldown; degraded/unusable handling | scripted probability/quality traces | reproducible episode counting |
| Controlled experiment | same ECG model/threshold/cadence/episode policy; perturb clean paired streams | fixed seeds; excess alerts/h, chatter, recheck, suppression | operational robustness; not ectopy sensitivity |

# 11. Centralized Model Development Plan

| Checkpoint | Input allowed | Action | Output | Stop condition |
| --- | --- | --- | --- | --- |
| Baseline ready | G0-G6 PASS, train/val only | majority(train prevalence), LR, RF | E01 baseline report | pipeline cannot produce stable metrics |
| CNN development | train + validation | MODEL_V1 exact architecture, AdamW, 1e-3, wd1e-4, bs64, max50, patience7 | seed-specific validation logs | preprocessing or split changes |
| Release seed | same | train 20260927; keep best validation AUPRC checkpoint | candidate MODEL_V1 | architecture/preprocess must be frozen first |
| Robustness seeds | train + validation | 20260928/20260929, report mean±SD | development stability summary | never select release checkpoint from these |
| Model freeze | validation evidence only | hash checkpoint/config/preprocess/test vector | MODEL_V1 package | any code/config change => MODEL_V2 |
| Calibration | calibration only | temperature + F1 threshold | CAL_V1 | architecture changes forbidden |
| Internal test | internal test only | one locked run + predictions/bootstrap | internal_test final | no post-test tuning |
| External/robustness | INCART/NSTDB | one locked external + predeclared noise study | E05/E06 | do not adapt and still call it external |

# 12. Federated Learning Plan

| Step | Implementation | Invariant | Evidence |
| --- | --- | --- | --- |
| Toy aggregation | 2 tiny clients with hand-computable parameters | weighted aggregation equals analytical result | toy_aggregation.json |
| Flower scaffold | ClientApp/ServerApp/task adapter against toy model | serialization/state loading deterministic | fl_smoke logs |
| MODEL_V1 adapter | same model/loss/preprocess contract | central and client test-vector logits match | model_adapter_audit.json |
| Client construction | 8 sites from whole train patients only | patient appears in exactly one site; held-out patients never clients | CLIENTS_IID_V1.csv + audit |
| FedAvg IID | 50 rounds, all 8 clients, 1 local epoch, bs64, AdamW, weighted model-delta average | validation only during config development | E09 fl_iid |
| Non-IID | label, quantity, feature/noise; combined only if full scope remains | same patient pool/model/budget except intended factor | E10-E12 |
| FedProx | local proximal objective; mu {0.001,0.01,0.1} tuned label-skew validation | mu=0 matches FedAvg local objective; all other variables matched | E13 |
| Reporting | global, mean/median/worst-client AUPRC, F1, rounds-to-best, bytes | synthetic-site language everywhere | FL evidence package |

Implementation note: use current Flower App/Simulation Runtime conventions rather than legacy APIs. Day 1 environment verification records the installed Flower version; the FL scaffold is isolated behind federated/ so framework updates cannot alter labels, preprocessing or model code.

# 13. Privacy / Secure Aggregation Plan

| Phase | Prerequisite | Work | PASS evidence | Claim boundary |
| --- | --- | --- | --- | --- |
| Threat model | G11 FedAvg correct | document protected asset: individual clear client update; list non-goals | docs/privacy_threat_model.md | not anonymity, DP, attack-proofing or production certification |
| SecAgg+ setup | plain aggregation correct | configure Flower SecAgg+ with 8 simulated clients and threshold/dropout settings | config + key/setup log | simulation protocol demonstration |
| Correctness | instrumented known update round | aggregate equals unprotected reference within tolerance | aggregate_correctness.json | aggregate correctness only |
| Server visibility | instrument server aggregation interface | no individual clear update object exposed at protected aggregation point | server_visibility_audit.json | narrow v2.2 privacy claim |
| Overhead | stable protected run | runtime, bytes, completion rate, failures | privacy_report | overhead on this 8-client simulation |
| Fallback | SecAgg+ cannot pass | remove implemented privacy claim and retain threat-model discussion | release limitation entry | never ship unverifiable “privacy enabled” text |

# 14. Gateway / Deployment / API / Dashboard Plan

| Layer | Build order | Contract | Verification |
| --- | --- | --- | --- |
| Gateway replay | mock model first, then MODEL_V1 | window ndarray + quality/context -> typed result | deterministic replay log |
| Deploy artifact | FP32 mandatory; INT8 only if reliable | same input/output semantics | test-set prediction delta + artifact hash |
| Benchmark | after warm-up, >=1000 windows | model size, params, peak RAM, p50/p95 latency, throughput | edge_report |
| API | schema first with mock; real model later | POST /v1/infer-window + optional WS wrapper | 400/422/500 + IDs + calibration_domain tests |
| Dashboard | after enum/API freeze | waveform, quality, episode state, technical metadata, research panel | state-wording tests + replay screenshots |
| Wearable | serial reference transport | ESP32 acquisition timestamps remain authoritative | loss/gap/sync/session manifest evidence |
| Final demo | recorded replay always available; live optional in addition | same code path as evidence | one-command start + saved demo stream |

# 15. Testing and Validation Plan

| Test family | When | Mandatory assertions | Failure blocks |
| --- | --- | --- | --- |
| Contract/schema | before consumers | required fields, types, enum versions, IDs | all downstream |
| Data validation | during acquisition | version/hash/channel/annotation census/duplicates | G3 |
| Leakage/split | before windows/model | patient disjointness, 201/202 same group, windows built after split | G5 |
| Causality | test-first with preprocessing | future append unchanged, chunk equivalence, no filtfilt, gap rules | G6 |
| Window/quality/sync | with preprocessing | 10s/5s exact boundaries, state semantics, alignment tolerance | G6/G9 |
| Baseline/model | with training | train-only prevalence/scalers/pos_weight, deterministic checkpoint/test vector | G7/G8 |
| Statistics | before test | bootstrap resamples patients and recomputes pooled metrics; patient-macro F1 defined | G10 |
| Fusion/episodes | test-first | state table, K2/M2/cooldown30, degraded/unusable rules | G9 |
| FL | before real FL | analytical FedAvg, client isolation, FedProx mu=0 equivalence | G11/G13 |
| Privacy | after plain FL | aggregate correctness + server visibility | G14 |
| API/UI | before e2e | typed schema/errors and safe labels | G18/G19 |
| Replay/e2e | before release | same recorded stream reproduces results and logs | G21 |
| Clean environment | release | bootstrap/test/smoke on CPU | G20/G22 |

# 16. Freeze Map and Change-Control Rules

| Freeze | When | Immutable after freeze | Still allowed | Change invalidates |
| --- | --- | --- | --- | --- |
| F0 Scope/RQs | G0 | target, claim boundary, dataset roles | implementation detail within contracts | all downstream evidence if scientific scope changes |
| F1 Hardware/data contract | G1 | fields, units, timestamp semantics, config version | bug fix via version bump | wearable/sync/API evidence |
| F2 Dataset versions | G2-G3 | source versions/hashes/lead exclusions | re-download same hash | split and all model runs |
| F3 Label map | G4 | AAMI_SVF_MAP_V1 + target rules | no symbol additions | all supervised runs/external report |
| F4 Split | G5 | patient membership of train/val/cal/test | none except versioned new split | all central/FL/model results |
| F5 Preprocess | G6 | PREPROC_V1 + GAP_POLICY_V1 + window semantics | performance optimization preserving output within tolerance | all model/evaluation/deployment evidence |
| F6 Baselines | G7 | feature definitions/baseline configs for comparison | report formatting | baseline comparison |
| F7 MODEL_V1 | G8 | architecture/weights/input/checkpoint hash | wrapper/export only if predictions preserved | calibration/test/FL/deployment |
| F8 Calibration | G10 before test | temperature/threshold/CAL_V1 | display formatting | episode metrics/test/external |
| F9 Internal test | G10 | test predictions/report | error analysis only | cannot retune without new protocol/version |
| F10 External | after E06 | primary INCART result | post-hoc exploratory work clearly separated | external-generalization claim if adapted |
| F11 FL config/clients | G11/G12 | client manifests, core rounds/budgets | logging | FL comparison evidence |
| F12 FedProx | G13 | selected mu | none for primary comparison | FedProx report |
| F13 Privacy | G14 | SecAgg+ config/claim wording | instrumentation that does not alter protocol | privacy report |
| F14 Deployment | G15 | deploy artifact hash/runtime config | hardware-independent UI | benchmark/e2e |
| F15 Release | G22 | all artifact hashes and limitations | no scientific changes | release identity |

# 17. Experiment Execution Order

| ID | Objective | Prerequisite | Data | System | Metrics | Artifact | Allowed conclusion | Unlocks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| E01 | Baseline sanity | G6 | MIT-BIH train/val | Majority/LR | AUPRC/F1 | baseline_report | establish floor only | E02 |
| E02 | Neural gain | E01 + G6 | MIT-BIH train/val | MODEL_V1 candidates | val AUPRC | model_selection | compare model families | G8/E03 |
| E07 | Multimodal engineering | BIDMC loader+quality | BIDMC | context pipeline | alignment/rate error | bidmc_report | engineering compatibility | E08 |
| E03 | Calibration | G8 | MIT-BIH calibration | MODEL_V1 | Brier/ECE + threshold | CAL_V1 | MIT-BIH source calibration | E04/E08 |
| E04 | Internal generalization | E03/F8 | MIT-BIH test | MODEL_V1 | AUPRC/F1/CI | internal_test | patient-disjoint internal performance | E05/E06 |
| E05 | Noise robustness | G8/F7 | NSTDB/noise-mixed | MODEL_V1 | metric degradation | noise_report | noise sensitivity | - |
| E06 | External robustness | G8/F7 + map/lead frozen | INCART | MODEL_V1 | AUPRC/F1/CI | external_report | cross-dataset robustness | - |
| E08 | Quality-aware robustness | E07+E03+G9 harness | BIDMC+WEARABLE perturbations | same MODEL_V1 + context | excess alerts/h/chatter | quality_aware_alert | operational robustness only | - |
| E09 | FedAvg IID | G8 + toy FL | MIT-BIH train clients | MODEL_V1/FedAvg | global/worst AUPRC | fl_iid | federated baseline | E10-E12 |
| E10 | Label skew | E09 | same train pool | FedAvg | global/client metrics | fl_label | label-heterogeneity effect | E13 tune |
| E11 | Quantity skew | E09 | same train pool | FedAvg | global/client metrics | fl_quantity | quantity imbalance effect | E13 |
| E12 | Feature/noise skew | E09 | same train pool | FedAvg | global/client metrics | fl_feature | feature/noise heterogeneity effect | E13 |
| E13 | FedProx | G12 + selected mu from label-skew val | same manifests | FedProx | paired differences | fedprox_report | algorithm effect under matched settings | E14 |
| E14 | SecAgg+ | G11 minimum; final after stable FL | chosen frozen FL condition | FedAvg+SecAgg+ | runtime/bytes/correctness | privacy_report | protocol overhead/boundary | - |
| E15 | Gateway | G8/F7 | MIT-BIH test replay | deploy artifact | latency/RAM/delta | edge_report | gateway feasibility | E16/e2e |
| E16 | Wearable domain | G1+G6+gateway | WEARABLE_V1 | locked pipeline | quality/latency/distributions | wearable_report | domain compatibility only | Final demo |

# 18. G0–G22 Gate Map

| Gate | Purpose | Prerequisites | Artifacts/tests | PASS | FAIL | Recovery | Blocks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| G0 | Scope freeze | source reconciliation + coverage map | SOURCE_AUTHORITY + RQs/non-scope | all locked items mapped | ambiguity | repair plan; no modeling | all |
| G1 | Hardware/data contract | bench plan + schema | contract + firmware/packet evidence | fields/types/timestamps defined; verification items recorded | sensor semantics unknown | bench/version contract | wearable |
| G2 | Dataset acquisition | download scripts | dataset manifests/hashes | exact versions parse | missing/corrupt | redownload/fix loader | G3+ |
| G3 | Dataset validation | G2 | validation + lead exclusion reports | schema/channel/annotation checks pass | unexpected source facts | block and reconcile | G4+ |
| G4 | Label freeze | symbol census | AAMI_SVF_MAP_V1 tests | all symbols handled by allowlist/exclusion | ambiguous target | map version before training | model |
| G5 | Split/leakage | G4 grouping | MITDB_SPLIT_V1 + audits | zero overlap; 201/202 same group | leakage | regenerate before any evidence | model/FL |
| G6 | Preprocess pass | G5 + causal modules | causality/gap/window/QC reports | all future-append/chunk tests pass | future dependence | replace transform | model |
| G7 | Baseline pass | G6 | E01 report | pipeline produces reproducible metrics | pipeline failure | debug data/features | G8 |
| G8 | ECG model lock | G7 | MODEL_V1 hash/config/test vector | reproducible validation acceptance | unstable | simplify/tune val only | cal/FL/edge |
| G9 | Multimodal context | context + episode + perturb harness | BIDMC + E08 + state tests | reproducible paired experiment and exact episode tests | undefined alert counting/false claim | fix context only | final multimodal claim |
| G10 | Central eval freeze | G8 + CAL_V1 | calibration + internal test | threshold/checkpoint locked; test one-shot | post-test tuning | new version/test policy | final metrics |
| G11 | FedAvg | toy equivalence + G8 | IID FL report | aggregation correct + stable validation | aggregation bug | block advanced FL | G12+ |
| G12 | Non-IID | G11 | manifests + matched reports | patient integrity + intended factor only | confounded clients | rebuild manifests | G13 |
| G13 | FedProx | G12 + mu selection | matched comparison | only proximal objective differs | unmatched settings | rerun matched | FL result |
| G14 | Privacy | G11 stable FL | SecAgg+ report | aggregate correct; server protected interface lacks individual clear update | unsupported claim | fix or remove implementation claim | release privacy |
| G15 | Edge benchmark | G8 | gateway artifact/report | size/RAM/p50-p95/throughput/delta measured | no deployable artifact | Python gateway fallback | G21 |
| G16 | Wearable validation | G1/G6 | WEARABLE report | same canonical pipeline accepts hardware | hidden alternate pipeline | fix ingest/integration | G21 |
| G17 | Explainability | G8/G10 | IG report | zero baseline, 64 GL, signed+abs overlay, fixed cases | method drift | fix or omit UI use | viva |
| G18 | API | schema + real model adapter | OpenAPI/API test report | typed outputs/errors/IDs pass | schema drift | fix before dashboard | G19/G21 |
| G19 | Dashboard | G18 + episode enums | UI state test/screens | exact safe wording | diagnostic wording | block release | G21 |
| G20 | Reproducibility | all runnable components | clean-run report | CPU smoke reproduces IDs/tolerance | manual dependency | lock env/scripts | G22 |
| G21 | Final integration | G15,G16,G18,G19 | recorded replay/live evidence | stream→dashboard works without undocumented step | integration failure | use fallback level | G22 |
| G22 | Final release | mandatory gates/evidence | release_manifest + evidence index | all required artifacts or explicit fallback omissions | missing evidence | do not call complete | submission |

# 19. Exact Day-1 Bootstrap

Day 1 ends with one fixture-driven smoke path and a committed environment/authority skeleton. It does not install or train the full ML stack yet.

# 0. Create repository
mkdir nhm && cd nhm
git init
mkdir -p contracts configs datasets manifests preprocessing features models fusion training federated privacy evaluation deployment api dashboard tests/fixtures experiments reports docs scripts release

# 1. Create Python environment (Python 3.11.x required by this plan)
python3.11 -m venv .venv
source .venv/bin/activate
python -m pip install --upgrade pip
python -m pip install pytest ruff pydantic pyyaml numpy
python --version > reports/day1_python_version.txt
python -m pip freeze > reports/day1_packages.txt

# 2. Create project control files
touch README.md .gitignore pyproject.toml Makefile
printf "__pycache__/\n.venv/\ndata/\n*.pt\n*.pth\n.env\n" > .gitignore

# 3. Create initial contract/config/fixture files
# (populate from v2.2, not from invention)
touch docs/SOURCE_AUTHORITY.md docs/freeze_map.md docs/do_not_start.md
touch configs/base.yaml contracts/sample_schema_v1.json
touch tests/fixtures/session_v1.jsonl tests/test_smoke.py scripts/smoke_fixture.py

# 4. Run formatting/lint/test policy
ruff check .
pytest -q
python scripts/smoke_fixture.py --input tests/fixtures/session_v1.jsonl --out reports/day1_smoke.json

# 5. Save first artifact and commit
python -m pip freeze > requirements.day1.lock.txt
git add .
git commit -m "bootstrap: authority, contracts, fixtures, smoke test"

| Day-1 item | Exact result required |
| --- | --- |
| Environment | Python 3.11.x venv created; exact resolved packages saved. |
| Authority | SOURCE_AUTHORITY.md identifies v2.2 as technical authority and originals as supporting only. |
| Repository | All top-level v2.2 directories exist plus release/ control folder. |
| Config | base.yaml has project/version/seed-path placeholders; no scientific defaults invented. |
| Fixture | one canonical JSONL session fixture with timestamps, ECG/PPG/null context and quality enums. |
| Contract test | fixture validates required schema fields and monotonic timestamps. |
| Smoke | fixture -> mock inference -> deterministic monitoring state -> JSON report succeeds. |
| Evidence | reports/day1_smoke.json, Python/package capture, first Git commit. |
| Do not start | real dataset split, model training, Flower, SecAgg+, dashboard styling, MCU optimization. |

Day-1 success = a clean clone can create the venv, run pytest, and produce the same fixture smoke artifact without any undocumented manual step.

# 20. Day 1–14 Detailed Plan

| Day | Primary objective | Tasks | Artifacts | Tests/review | Gate | Do not start yet |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Bootstrap + authority + fixture slice | T001-T003,T005 | repo/control files; fixture smoke | pytest + smoke JSON | G0 skeleton | Do not download/train yet |
| 2 | Hardware bench risk + packet/timestamp contract | T004 | hardware_bench.md; packet schema; sample capture | rate/jitter/sequence-gap checks | G1 candidate | No volunteer collection |
| 3 | MIT-BIH loader + manifest | T006 | mitdb_v1.yaml; raw validation | version/hash/channel-name checks | G2 partial | No split yet |
| 4 | INCART/NSTDB/BIDMC loaders | T007 | three manifests + validation summaries | parse/sampling/channel/annotation checks | G2 | No external/model use |
| 5 | Lead policy + symbol census/map | T006-T008 | exclusion list; census CSVs; mapper | allowlist tests all symbols | G3-G4 prep | No windows/model |
| 6 | Patient grouping + split algorithm | T009 | MITDB_SPLIT_V1 draft | 201/202 same group; class coverage report | G5 prep | Do not regenerate based on metrics |
| 7 | Leakage audit + split freeze | T010 | split_audit.json; frozen manifest hash | zero overlap/neighborhood checks | G5 | No model before PASS |
| 8 | Causal resampler test-first | T011 | resampler.py + config | future-append + chunk equivalence | G6 prep | No convenience centered resampler |
| 9 | Gaps + ECG filter | T012 | gaps.py/ecg.py | short-gap ZOH exact; long-gap reset; impulse causality | G6 prep | No filtfilt |
| 10 | PPG filter/sync/quality skeleton | T012-T013 | ppg.py/sync.py/quality.py | synthetic pulses/offsets/flatline/clipping | G6/G9 prep | No learned fusion |
| 11 | Window builder + target examples | T013 | windowing.py + cached tiny fixture dataset | 10s/5s/right-edge/label-boundary tests | G6 prep | No real cache before split hash embedded |
| 12 | End-to-end causal pipeline audit | T010-T013 | preprocess test report | all leakage/causality tests together | G6 | Model remains blocked if any failure |
| 13 | Classical feature library + train-only transformers | T014 | features/ecg.py + scaler contract | fit-scope tests | G7 prep | No test fitting |
| 14 | Baseline runner + review checkpoint | T014 | E01 config/report on train/val | majority training-only assertion + LR/RF smoke | G7 candidate | No CNN until independent verification of G0-G6 |

# 21. Week-by-Week Solo Schedule

| Week | Core objective | Tasks | Expected gates | Major risk | Latest-safe-start note |
| --- | --- | --- | --- | --- | --- |
| W1 | Bootstrap, contracts, hardware risk, dataset acquisition | T001-T007 | G0-G3 candidates | Hardware semantics/dataset mismatch | Hardware bench must start now |
| W2 | Label/split/leakage + causal preprocessing | T008-T013 | G4-G6 | Hidden leakage/resampler state | G6 must pass by end W2 |
| W3 | Classical baselines + runner + context pipeline | T014,T021-T022 | G7 + G9 harness | quality thresholds / feature bugs | - |
| W4 | CNN MODEL_V1 development + FL toy scaffold | T015,T024 | G8 candidate | overfit/interface drift | MODEL_V1 training latest start |
| W5 | MODEL_V1 freeze + calibration + internal eval prep | T016-T018 | G8/G10 | small calibration n | - |
| W6 | Internal test + NSTDB + INCART | T018-T020 | G10 + external evidence | domain collapse | no retuning after test |
| W7 | Finalize BIDMC/context robustness; client manifests | T021-T025 | G9 + G11 prep | alert metric ambiguity | real FedAvg latest start |
| W8 | FedAvg IID + label/quantity non-IID | T025-T026 | G11/G12 partial | small patients/site | - |
| W9 | Feature/noise non-IID + FedProx tune/compare | T026-T027 | G12/G13 | confounded budgets | - |
| W10 | SecAgg+ + gateway export | T028-T029 | G14/G15 prep | framework integration/conversion | privacy work latest start |
| W11 | Gateway benchmark + API real model + IG/error analysis | T029,T031,T032 | G15/G17/G18 | runtime drift | - |
| W12 | Wearable synchronized sessions + domain report | T030 | G16 | hardware/consent delays | wearable e2e latest start |
| W13 | Dashboard + recorded/live e2e | T033-T034 | G19/G21 candidate | UI semantics/integration | - |
| W14 | Regression reruns + communication/resource reports | T026-T035 | G20 candidate | late config drift | no new features |
| W15 | Clean-environment release rehearsal + viva/evidence map | T035-T036 | G20/G21 | manual dependency | scope frozen |
| W16 | Final buffer, release manifest, submission package | T036 | G22 | missing evidence | only defect fixes |

Effort uncertainty: public-data work is usually predictable; hardware integration, SecAgg+ and platform-specific deployment are not. Reserve Weeks 15–16 primarily as integration/recovery buffer, not planned feature development.

# 22. Primary Implementation Task Packets

## T001 — Repository/bootstrap and source authority lock

| Field | Packet definition |
| --- | --- |
| TASK ID | T001 |
| PHASE | BOOT |
| OBJECTIVE | Initialize repository and reproducible development shell. |
| RELEVANT v2.2 SECTIONS | v2.2 Sections 30,32; Solo Prompt 12,24,32 |
| PREREQUISITES | None |
| FILES TO INSPECT | v2.2 + solo prompt; local Python |
| FILES TO CREATE/MODIFY | Environment files + smoke harness |
| INPUTS / OUTPUTS | Inputs: v2.2 + solo prompt; local Python. Outputs: Environment files + smoke harness. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | No scientific constants beyond version IDs; record host facts, do not guess. |
| TESTS | pytest/ruff/smoke |
| COMMANDS / RUN STEPS | create venv; install minimal tools; pytest; smoke |
| EXPECTED ARTIFACTS | env capture + first commit |
| ACCEPTANCE CRITERIA | clean clone can repeat Day-1 smoke |
| RISKS | dependency/tool drift |
| RECOVERY | pin resolved versions; preserve artifact |
| WHAT MUST NOT CHANGE | Scientific scope, source authority |
| GATE / FREEZE IMPACT | G0 |
| NEXT UNLOCKED DEPENDENCY | T002-T005 |

## T002 — Requirement registry and coverage map

| Field | Packet definition |
| --- | --- |
| TASK ID | T002 |
| PHASE | BOOT |
| OBJECTIVE | Translate every mandatory v2.2 requirement into task/gate/evidence IDs. |
| RELEVANT v2.2 SECTIONS | All locked spec + DoD |
| PREREQUISITES | T001 |
| FILES TO INSPECT | v2.2 tables/appendices |
| FILES TO CREATE/MODIFY | requirements_v22.csv + freeze/do-not-start maps |
| INPUTS / OUTPUTS | Inputs: v2.2 tables/appendices. Outputs: requirements_v22.csv + freeze/do-not-start maps. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | No omission by “implicit coverage”. |
| TESTS | coverage completeness script/manual audit |
| COMMANDS / RUN STEPS | run coverage audit |
| EXPECTED ARTIFACTS | coverage matrix |
| ACCEPTANCE CRITERIA | zero unmapped mandatory items |
| RISKS | source version mismatch |
| RECOVERY | re-read source and version matrix |
| WHAT MUST NOT CHANGE | v2.2 authority |
| GATE / FREEZE IMPACT | G0 |
| NEXT UNLOCKED DEPENDENCY | All tasks |

## T003 — Canonical hardware/data/API/label contract skeletons

| Field | Packet definition |
| --- | --- |
| TASK ID | T003 |
| PHASE | CONTRACT |
| OBJECTIVE | Canonical hardware/data/API/label contract skeletons |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | contracts/HARDWARE_DATA_CONTRACT_V1.md, contracts/sample_schema_v1.json, contracts/API_SCHEMA_V1.json, contracts/LABEL_SCHEMA_V1.md |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: contracts/HARDWARE_DATA_CONTRACT_V1.md, contracts/sample_schema_v1.json, contracts/API_SCHEMA_V1.json, contracts/LABEL_SCHEMA_V1.md. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | schema fixtures validate; versions present |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | contracts/HARDWARE_DATA_CONTRACT_V1.md, contracts/sample_schema_v1.json, contracts/API_SCHEMA_V1.json, contracts/LABEL_SCHEMA_V1.md |
| ACCEPTANCE CRITERIA | schema fixtures validate; versions present |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G1 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T004 — Bench hardware verification and firmware packet contract

| Field | Packet definition |
| --- | --- |
| TASK ID | T004 |
| PHASE | HARDWARE |
| OBJECTIVE | Eliminate hardware semantics uncertainty before real collection. |
| RELEVANT v2.2 SECTIONS | v2.2 Sec 4,43 |
| PREREQUISITES | T001,T003 |
| FILES TO INSPECT | actual boards/firmware |
| FILES TO CREATE/MODIFY | bench measurements + contract updates |
| INPUTS / OUTPUTS | Inputs: actual boards/firmware. Outputs: bench measurements + contract updates. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | VERIFICATION REQUIRED values must be measured or left unresolved. |
| TESTS | rate/jitter/CRC/sequence tests |
| COMMANDS / RUN STEPS | capture 10-min traces |
| EXPECTED ARTIFACTS | hardware_bench.md + config hash |
| ACCEPTANCE CRITERIA | all G1 semantics known/versioned |
| RISKS | board/firmware unavailable |
| RECOVERY | continue software with fixtures; block wearable evidence |
| WHAT MUST NOT CHANGE | No invented ADC/gain/register facts |
| GATE / FREEZE IMPACT | G1 |
| NEXT UNLOCKED DEPENDENCY | T030 |

## T005 — Fixture vertical slice 0

| Field | Packet definition |
| --- | --- |
| TASK ID | T005 |
| PHASE | SLICE0 |
| OBJECTIVE | Fixture vertical slice 0 |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | tests/fixtures/session_v1.jsonl, deployment/mock_inference.py, fusion/state_machine.py, api/app.py |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: tests/fixtures/session_v1.jsonl, deployment/mock_inference.py, fusion/state_machine.py, api/app.py. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | fixture→state→API smoke passes |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | tests/fixtures/session_v1.jsonl, deployment/mock_inference.py, fusion/state_machine.py, api/app.py |
| ACCEPTANCE CRITERIA | fixture→state→API smoke passes |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G1 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T006 — MIT-BIH exact-version acquisition/manifest/MLII selection

| Field | Packet definition |
| --- | --- |
| TASK ID | T006 |
| PHASE | DATA |
| OBJECTIVE | MIT-BIH exact-version acquisition/manifest/MLII selection |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | datasets/mitdb.py, manifests/datasets/mitdb_v1.yaml |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: datasets/mitdb.py, manifests/datasets/mitdb_v1.yaml. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | hash/version/channel/exclusion report |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | datasets/mitdb.py, manifests/datasets/mitdb_v1.yaml |
| ACCEPTANCE CRITERIA | hash/version/channel/exclusion report |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G2-G3 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T007 — INCART/NSTDB/BIDMC acquisition and role-specific loaders

| Field | Packet definition |
| --- | --- |
| TASK ID | T007 |
| PHASE | DATA |
| OBJECTIVE | INCART/NSTDB/BIDMC acquisition and role-specific loaders |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | datasets/incart.py, datasets/nstdb.py, datasets/bidmc.py, manifests/datasets/*.yaml |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: datasets/incart.py, datasets/nstdb.py, datasets/bidmc.py, manifests/datasets/*.yaml. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | dataset validation reports |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | datasets/incart.py, datasets/nstdb.py, datasets/bidmc.py, manifests/datasets/*.yaml |
| ACCEPTANCE CRITERIA | dataset validation reports |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G2-G3 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T008 — Shared AAMI_SVF_MAP_V1 and source symbol census

| Field | Packet definition |
| --- | --- |
| TASK ID | T008 |
| PHASE | LABEL |
| OBJECTIVE | Freeze identical MIT-BIH/INCART beat mapping. |
| RELEVANT v2.2 SECTIONS | v2.2 Sec 9 |
| PREREQUISITES | T006,T007 |
| FILES TO INSPECT | raw annotations |
| FILES TO CREATE/MODIFY | mapper + symbol census |
| INPUTS / OUTPUTS | Inputs: raw annotations. Outputs: mapper + symbol census. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Any unlisted beat symbol excluded. |
| TESTS | allowlist exhaustive tests |
| COMMANDS / RUN STEPS | build census; run pytest labels |
| EXPECTED ARTIFACTS | census + LABEL_SCHEMA |
| ACCEPTANCE CRITERIA | all source symbols accounted for |
| RISKS | unexpected symbol |
| RECOVERY | exclude by default; version bump only before model freeze |
| WHAT MUST NOT CHANGE | AAMI_SVF_MAP_V1 semantics |
| GATE / FREEZE IMPACT | G4 |
| NEXT UNLOCKED DEPENDENCY | T009-T015,T020 |

## T009 — Patient grouping and MITDB_SPLIT_V1

| Field | Packet definition |
| --- | --- |
| TASK ID | T009 |
| PHASE | SPLIT |
| OBJECTIVE | Patient grouping and MITDB_SPLIT_V1 |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | datasets/grouping.py, manifests/splits/MITDB_SPLIT_V1.csv |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: datasets/grouping.py, manifests/splits/MITDB_SPLIT_V1.csv. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | zero overlap; 201/202 together; patient counts saved |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | datasets/grouping.py, manifests/splits/MITDB_SPLIT_V1.csv |
| ACCEPTANCE CRITERIA | zero overlap; 201/202 together; patient counts saved |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G5 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T010 — Leakage audit harness

| Field | Packet definition |
| --- | --- |
| TASK ID | T010 |
| PHASE | LEAKAGE |
| OBJECTIVE | Leakage audit harness |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | tests/test_leakage.py, evaluation/leakage_audit.py |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: tests/test_leakage.py, evaluation/leakage_audit.py. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | all invariants pass on synthetic and manifest inputs |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | tests/test_leakage.py, evaluation/leakage_audit.py |
| ACCEPTANCE CRITERIA | all invariants pass on synthetic and manifest inputs |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G5-G6 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T011 — Stateful causal resampler PREPROC_V1

| Field | Packet definition |
| --- | --- |
| TASK ID | T011 |
| PHASE | PREPROC |
| OBJECTIVE | Implement causal streaming resampler. |
| RELEVANT v2.2 SECTIONS | v2.2 Sec 8.2 |
| PREREQUISITES | T006,T010 |
| FILES TO INSPECT | source samples/timestamps |
| FILES TO CREATE/MODIFY | 250-Hz stream + state metadata |
| INPUTS / OUTPUTS | Inputs: source samples/timestamps. Outputs: 250-Hz stream + state metadata. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | No future sample may affect output <=t; explicit group delay. |
| TESTS | future-append, chunk-equivalence |
| COMMANDS / RUN STEPS | run synthetic prefixes/chunks |
| EXPECTED ARTIFACTS | resampler_causality.json |
| ACCEPTANCE CRITERIA | tests within tolerance for 360→250 and 257→250 |
| RISKS | library convenience function is centered |
| RECOVERY | wrap lower-level causal polyphase/upfirdn with state |
| WHAT MUST NOT CHANGE | PREPROC causal invariant |
| GATE / FREEZE IMPACT | G6 |
| NEXT UNLOCKED DEPENDENCY | T013-T015,T020,T030 |

## T012 — Causal ECG/PPG filters and GAP_POLICY_V1

| Field | Packet definition |
| --- | --- |
| TASK ID | T012 |
| PHASE | PREPROC |
| OBJECTIVE | Causal ECG/PPG filters and GAP_POLICY_V1 |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | preprocessing/ecg.py, preprocessing/ppg.py, preprocessing/gaps.py |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: preprocessing/ecg.py, preprocessing/ppg.py, preprocessing/gaps.py. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | short-gap exact ZOH; long-gap reset/UNUSABLE; filter causality |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | preprocessing/ecg.py, preprocessing/ppg.py, preprocessing/gaps.py |
| ACCEPTANCE CRITERIA | short-gap exact ZOH; long-gap reset/UNUSABLE; filter causality |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G6 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T013 — Windowing, synchronization and quality

| Field | Packet definition |
| --- | --- |
| TASK ID | T013 |
| PHASE | WINDOW |
| OBJECTIVE | Windowing, synchronization and quality |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | preprocessing/windowing.py, preprocessing/sync.py, preprocessing/quality.py, configs/quality_v1.yaml |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: preprocessing/windowing.py, preprocessing/sync.py, preprocessing/quality.py, configs/quality_v1.yaml. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | 10s/5s boundaries, quality/sync fixture tests |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | preprocessing/windowing.py, preprocessing/sync.py, preprocessing/quality.py, configs/quality_v1.yaml |
| ACCEPTANCE CRITERIA | 10s/5s boundaries, quality/sync fixture tests |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G6 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T014 — Classical features and baselines

| Field | Packet definition |
| --- | --- |
| TASK ID | T014 |
| PHASE | BASE |
| OBJECTIVE | Classical features and baselines |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | features/ecg.py, models/baselines.py, training/train_baselines.py |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: features/ecg.py, models/baselines.py, training/train_baselines.py. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | majority from train only; LR/RF reports reproducible |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | features/ecg.py, models/baselines.py, training/train_baselines.py |
| ACCEPTANCE CRITERIA | majority from train only; LR/RF reports reproducible |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G7 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T015 — MODEL_V1 CNN and centralized runner

| Field | Packet definition |
| --- | --- |
| TASK ID | T015 |
| PHASE | MODEL |
| OBJECTIVE | Train exact MODEL_V1 under frozen data/preprocess. |
| RELEVANT v2.2 SECTIONS | v2.2 Sec 13,16 |
| PREREQUISITES | G7 |
| FILES TO INSPECT | train/val caches |
| FILES TO CREATE/MODIFY | checkpoint + logs |
| INPUTS / OUTPUTS | Inputs: train/val caches. Outputs: checkpoint + logs. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Exact architecture/hparams; seed policy fixed. |
| TESTS | shape, loss, deterministic test vector |
| COMMANDS / RUN STEPS | train primary + replicate seeds |
| EXPECTED ARTIFACTS | candidate checkpoint/logs |
| ACCEPTANCE CRITERIA | release checkpoint from seed 20260927 best val AUPRC |
| RISKS | overfit/instability |
| RECOVERY | simplify only through versioned validation-stage change |
| WHAT MUST NOT CHANGE | Test/cal/external untouched |
| GATE / FREEZE IMPACT | G8 |
| NEXT UNLOCKED DEPENDENCY | T016-T020,T025,T029 |

## T016 — MODEL_V1 freeze and test-vector package

| Field | Packet definition |
| --- | --- |
| TASK ID | T016 |
| PHASE | MODEL |
| OBJECTIVE | MODEL_V1 freeze and test-vector package |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | checkpoints/MODEL_V1.pt, configs/model_v1_frozen.yaml, tests/fixtures/model_v1_test_vector.npz |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: checkpoints/MODEL_V1.pt, configs/model_v1_frozen.yaml, tests/fixtures/model_v1_test_vector.npz. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | hash fixed; logits reproduce within tolerance |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | checkpoints/MODEL_V1.pt, configs/model_v1_frozen.yaml, tests/fixtures/model_v1_test_vector.npz |
| ACCEPTANCE CRITERIA | hash fixed; logits reproduce within tolerance |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G8 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T017 — Temperature scaling and threshold

| Field | Packet definition |
| --- | --- |
| TASK ID | T017 |
| PHASE | CAL |
| OBJECTIVE | Temperature scaling and threshold |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | evaluation/calibration.py, artifacts/CAL_V1.json |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: evaluation/calibration.py, artifacts/CAL_V1.json. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | calibration-only fit; patient count/domain captured |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | evaluation/calibration.py, artifacts/CAL_V1.json |
| ACCEPTANCE CRITERIA | calibration-only fit; patient count/domain captured |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G10 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T018 — Internal test + patient-cluster bootstrap

| Field | Packet definition |
| --- | --- |
| TASK ID | T018 |
| PHASE | EVAL |
| OBJECTIVE | Internal test + patient-cluster bootstrap |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | evaluation/metrics.py, evaluation/bootstrap.py, reports/internal_test.* |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: evaluation/metrics.py, evaluation/bootstrap.py, reports/internal_test.*. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | single locked test; 2000 patient-cluster replicates |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | evaluation/metrics.py, evaluation/bootstrap.py, reports/internal_test.* |
| ACCEPTANCE CRITERIA | single locked test; 2000 patient-cluster replicates |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G10 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T019 — NSTDB/noise robustness

| Field | Packet definition |
| --- | --- |
| TASK ID | T019 |
| PHASE | ROBUST |
| OBJECTIVE | NSTDB/noise robustness |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | evaluation/noise.py, reports/noise_robustness.* |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: evaluation/noise.py, reports/noise_robustness.*. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | predeclared noise protocol; degradation curves |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | evaluation/noise.py, reports/noise_robustness.* |
| ACCEPTANCE CRITERIA | predeclared noise protocol; degradation curves |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | post-G10 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T020 — Locked INCART external evaluation

| Field | Packet definition |
| --- | --- |
| TASK ID | T020 |
| PHASE | EXT |
| OBJECTIVE | Locked INCART external evaluation |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | evaluation/external_incart.py, reports/external_incart.* |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: evaluation/external_incart.py, reports/external_incart.*. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | same map/Lead II/preprocess/model; one primary run |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | evaluation/external_incart.py, reports/external_incart.* |
| ACCEPTANCE CRITERIA | same map/Lead II/preprocess/model; one primary run |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | post-G10 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T021 — BIDMC PPG/SpO2/HR engineering validation

| Field | Packet definition |
| --- | --- |
| TASK ID | T021 |
| PHASE | CTX |
| OBJECTIVE | BIDMC PPG/SpO2/HR engineering validation |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | evaluation/bidmc_context.py, reports/bidmc_multimodal_engineering.* |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: evaluation/bidmc_context.py, reports/bidmc_multimodal_engineering.*. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | alignment/rate/quality/missingness tests |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | evaluation/bidmc_context.py, reports/bidmc_multimodal_engineering.* |
| ACCEPTANCE CRITERIA | alignment/rate/quality/missingness tests |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G9 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T022 — Deterministic fusion and ALERT_POLICY_V1

| Field | Packet definition |
| --- | --- |
| TASK ID | T022 |
| PHASE | CTX |
| OBJECTIVE | Deterministic fusion and ALERT_POLICY_V1 |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | fusion/state_machine.py, fusion/episode_manager.py, configs/alert_policy_v1.yaml |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: fusion/state_machine.py, fusion/episode_manager.py, configs/alert_policy_v1.yaml. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | scripted state sequences pass exactly |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | fusion/state_machine.py, fusion/episode_manager.py, configs/alert_policy_v1.yaml |
| ACCEPTANCE CRITERIA | scripted state sequences pass exactly |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G9 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T023 — Controlled ECG-only vs quality-aware robustness experiment

| Field | Packet definition |
| --- | --- |
| TASK ID | T023 |
| PHASE | CTX |
| OBJECTIVE | Demonstrate operational value of multimodal quality/context. |
| RELEVANT v2.2 SECTIONS | v2.2 Sec 15.2 |
| PREREQUISITES | T017,T021,T022 |
| FILES TO INSPECT | paired clean/degraded streams |
| FILES TO CREATE/MODIFY | episode metrics report |
| INPUTS / OUTPUTS | Inputs: paired clean/degraded streams. Outputs: episode metrics report. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Same ECG model/threshold/cadence/debounce both arms; no ectopy efficacy claim. |
| TESTS | seeded perturbation replay |
| COMMANDS / RUN STEPS | run paired scenario matrix |
| EXPECTED ARTIFACTS | quality_aware_alert report |
| ACCEPTANCE CRITERIA | all scenarios reproducible; metrics trace to episodes |
| RISKS | noisy context worsens state behavior |
| RECOVERY | report negative result; inspect deterministic rule bug vs finding |
| WHAT MUST NOT CHANGE | No learned arrhythmia fusion |
| GATE / FREEZE IMPACT | G9 |
| NEXT UNLOCKED DEPENDENCY | Final RQ5 evidence |

## T024 — Toy aggregation and Flower scaffold

| Field | Packet definition |
| --- | --- |
| TASK ID | T024 |
| PHASE | FL |
| OBJECTIVE | Toy aggregation and Flower scaffold |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | federated/client_app.py, federated/server_app.py, federated/aggregation.py |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: federated/client_app.py, federated/server_app.py, federated/aggregation.py. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | analytical 2-client FedAvg equivalence |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | federated/client_app.py, federated/server_app.py, federated/aggregation.py |
| ACCEPTANCE CRITERIA | analytical 2-client FedAvg equivalence |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G11 prep |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T025 — Whole-patient client manifests + IID FedAvg

| Field | Packet definition |
| --- | --- |
| TASK ID | T025 |
| PHASE | FL |
| OBJECTIVE | Run real IID FedAvg with whole-patient sites. |
| RELEVANT v2.2 SECTIONS | v2.2 Sec 17 |
| PREREQUISITES | T016,T024,T009 |
| FILES TO INSPECT | MODEL_V1 + train patients |
| FILES TO CREATE/MODIFY | CLIENTS_IID_V1 + round logs |
| INPUTS / OUTPUTS | Inputs: MODEL_V1 + train patients. Outputs: CLIENTS_IID_V1 + round logs. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | 8 synthetic sites; no held-out patients. |
| TESTS | client disjointness + central adapter test |
| COMMANDS / RUN STEPS | flwr run configured app |
| EXPECTED ARTIFACTS | fl_iid report |
| ACCEPTANCE CRITERIA | aggregation correct and validation stable |
| RISKS | small sites / framework bug |
| RECOVERY | rebuild deterministic balanced manifest; not rows |
| WHAT MUST NOT CHANGE | MODEL_V1/preprocess unchanged |
| GATE / FREEZE IMPACT | G11 |
| NEXT UNLOCKED DEPENDENCY | T026-T028 |

## T026 — Label/quantity/feature non-IID experiments

| Field | Packet definition |
| --- | --- |
| TASK ID | T026 |
| PHASE | FL |
| OBJECTIVE | Label/quantity/feature non-IID experiments |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | manifests/clients/NONIID_*.csv, reports/fl_non_iid.* |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: manifests/clients/NONIID_*.csv, reports/fl_non_iid.*. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | matched total pool/budget; patient integrity |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | manifests/clients/NONIID_*.csv, reports/fl_non_iid.* |
| ACCEPTANCE CRITERIA | matched total pool/budget; patient integrity |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G12 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T027 — FedProx implementation and matched comparison

| Field | Packet definition |
| --- | --- |
| TASK ID | T027 |
| PHASE | FL |
| OBJECTIVE | Implement/tune FedProx under matched conditions. |
| RELEVANT v2.2 SECTIONS | v2.2 Sec 19 |
| PREREQUISITES | T026 |
| FILES TO INSPECT | same clients/model |
| FILES TO CREATE/MODIFY | frozen mu + matched reports |
| INPUTS / OUTPUTS | Inputs: same clients/model. Outputs: frozen mu + matched reports. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Only proximal term differs; tune on label-skew validation. |
| TESTS | mu=0 equivalence |
| COMMANDS / RUN STEPS | run candidates then frozen comparisons |
| EXPECTED ARTIFACTS | fedprox report |
| ACCEPTANCE CRITERIA | matched variable audit passes |
| RISKS | no benefit |
| RECOVERY | report negative/null result |
| WHAT MUST NOT CHANGE | Do not alter client manifests/budgets |
| GATE / FREEZE IMPACT | G13 |
| NEXT UNLOCKED DEPENDENCY | Final RQ3 evidence |

## T028 — Flower SecAgg+ correctness/overhead experiment

| Field | Packet definition |
| --- | --- |
| TASK ID | T028 |
| PHASE | PRIV |
| OBJECTIVE | Demonstrate SecAgg+ protocol behavior and overhead. |
| RELEVANT v2.2 SECTIONS | v2.2 Sec 20 |
| PREREQUISITES | G11 |
| FILES TO INSPECT | stable Flower FedAvg app |
| FILES TO CREATE/MODIFY | protected aggregation report |
| INPUTS / OUTPUTS | Inputs: stable Flower FedAvg app. Outputs: protected aggregation report. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Narrow claim only; instrument server interface. |
| TESTS | aggregate correctness/server visibility |
| COMMANDS / RUN STEPS | run protected and reference rounds |
| EXPECTED ARTIFACTS | privacy report |
| ACCEPTANCE CRITERIA | protected aggregate correct; no individual clear update at server interface |
| RISKS | framework incompatibility |
| RECOVERY | fix; otherwise emergency fallback removes claim |
| WHAT MUST NOT CHANGE | No broad privacy claims |
| GATE / FREEZE IMPACT | G14 |
| NEXT UNLOCKED DEPENDENCY | T036 |

## T029 — Gateway artifact and resource benchmark

| Field | Packet definition |
| --- | --- |
| TASK ID | T029 |
| PHASE | EDGE |
| OBJECTIVE | Gateway artifact and resource benchmark |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | deployment/export.py, deployment/benchmark.py, reports/edge_gateway.* |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: deployment/export.py, deployment/benchmark.py, reports/edge_gateway.*. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | size/RAM/p50-p95 latency/1000 windows/accuracy delta |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | deployment/export.py, deployment/benchmark.py, reports/edge_gateway.* |
| ACCEPTANCE CRITERIA | size/RAM/p50-p95 latency/1000 windows/accuracy delta |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G15 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T030 — Wearable ingest and domain-validation sessions

| Field | Packet definition |
| --- | --- |
| TASK ID | T030 |
| PHASE | WEAR |
| OBJECTIVE | Pass real synchronized hardware data through locked canonical path. |
| RELEVANT v2.2 SECTIONS | v2.2 Sec 22 |
| PREREQUISITES | T004,T013,T029 |
| FILES TO INSPECT | consented WEARABLE_V1 streams |
| FILES TO CREATE/MODIFY | wearable manifests + domain report |
| INPUTS / OUTPUTS | Inputs: consented WEARABLE_V1 streams. Outputs: wearable manifests + domain report. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | No disease/AAMI-SVF sensitivity claims. |
| TESTS | timestamp/sync/gap/quality/latency checks |
| COMMANDS / RUN STEPS | record per activity state; replay |
| EXPECTED ARTIFACTS | wearable_report |
| ACCEPTANCE CRITERIA | same preprocessing/API path; no hidden alternate code |
| RISKS | collection delay/poor PPG |
| RECOVERY | minimal safe sessions; report limits |
| WHAT MUST NOT CHANGE | Hardware contract and model frozen |
| GATE / FREEZE IMPACT | G16 |
| NEXT UNLOCKED DEPENDENCY | T034 |

## T031 — Integrated Gradients and error analysis

| Field | Packet definition |
| --- | --- |
| TASK ID | T031 |
| PHASE | XAI |
| OBJECTIVE | Integrated Gradients and error analysis |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | evaluation/explain.py, evaluation/error_analysis.py, reports/explainability_v1.* |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: evaluation/explain.py, evaluation/error_analysis.py, reports/explainability_v1.*. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | zero baseline; 64 GL; fixed case selection; convergence delta |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | evaluation/explain.py, evaluation/error_analysis.py, reports/explainability_v1.* |
| ACCEPTANCE CRITERIA | zero baseline; 64 GL; fixed case selection; convergence delta |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G17 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T032 — Typed API and versioned runtime contract

| Field | Packet definition |
| --- | --- |
| TASK ID | T032 |
| PHASE | API |
| OBJECTIVE | Typed API and versioned runtime contract |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | api/app.py, api/schemas.py, contracts/openapi_v1.json |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: api/app.py, api/schemas.py, contracts/openapi_v1.json. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | 400/422/500 semantics; IDs/domain returned |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | api/app.py, api/schemas.py, contracts/openapi_v1.json |
| ACCEPTANCE CRITERIA | 400/422/500 semantics; IDs/domain returned |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G18 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T033 — Dashboard and state mapping

| Field | Packet definition |
| --- | --- |
| TASK ID | T033 |
| PHASE | UI |
| OBJECTIVE | Dashboard and state mapping |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | dashboard/, tests/test_dashboard_states.py |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: dashboard/, tests/test_dashboard_states.py. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | all API states mapped; no diagnosis wording |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | dashboard/, tests/test_dashboard_states.py |
| ACCEPTANCE CRITERIA | all API states mapped; no diagnosis wording |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G19 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T034 — Replay/live end-to-end integration

| Field | Packet definition |
| --- | --- |
| TASK ID | T034 |
| PHASE | E2E |
| OBJECTIVE | Replay/live end-to-end integration |
| RELEVANT v2.2 SECTIONS | Relevant v2.2 section(s) for this subsystem |
| PREREQUISITES | Previous dependency/gate in Sections 4–5 |
| FILES TO INSPECT | locked configs, manifests and upstream artifacts |
| FILES TO CREATE/MODIFY | scripts/run_replay.py, tests/test_e2e_replay.py, reports/e2e_demo.* |
| INPUTS / OUTPUTS | Inputs: locked configs, manifests and upstream artifacts. Outputs: scripts/run_replay.py, tests/test_e2e_replay.py, reports/e2e_demo.*. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Preserve all locked v2.2 invariants; no held-out tuning; version any contract change. |
| TESTS | recorded stream→dashboard reproducible |
| COMMANDS / RUN STEPS | run targeted pytest + task-specific script/runner |
| EXPECTED ARTIFACTS | scripts/run_replay.py, tests/test_e2e_replay.py, reports/e2e_demo.* |
| ACCEPTANCE CRITERIA | recorded stream→dashboard reproducible |
| RISKS | interface drift, leakage or unreproducible local state |
| RECOVERY | stop downstream work, correct root cause, rerun regression and affected gate |
| WHAT MUST NOT CHANGE | target/map/split/preprocess/model/claim boundary without versioned change |
| GATE / FREEZE IMPACT | G21 |
| NEXT UNLOCKED DEPENDENCY | See dependency graph/critical path. |

## T035 — Clean-environment reproducibility

| Field | Packet definition |
| --- | --- |
| TASK ID | T035 |
| PHASE | REPRO |
| OBJECTIVE | Prove clean-environment reproducibility. |
| RELEVANT v2.2 SECTIONS | v2.2 Sec 30,44 |
| PREREQUISITES | all mandatory components |
| FILES TO INSPECT | fresh checkout + lockfile |
| FILES TO CREATE/MODIFY | clean-run report |
| INPUTS / OUTPUTS | Inputs: fresh checkout + lockfile. Outputs: clean-run report. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | No manual edits or hidden local files. |
| TESTS | full test + CPU smoke |
| COMMANDS / RUN STEPS | bootstrap then run smoke/eval subset |
| EXPECTED ARTIFACTS | repro report |
| ACCEPTANCE CRITERIA | artifact IDs/metrics within declared tolerance |
| RISKS | missing dependency/path |
| RECOVERY | fix scripts/locks; no manual workaround |
| WHAT MUST NOT CHANGE | Scientific outputs unchanged |
| GATE / FREEZE IMPACT | G20 |
| NEXT UNLOCKED DEPENDENCY | T036 |

## T036 — Final evidence/release manifest

| Field | Packet definition |
| --- | --- |
| TASK ID | T036 |
| PHASE | REL |
| OBJECTIVE | Assemble immutable release/evidence package. |
| RELEVANT v2.2 SECTIONS | v2.2 Sec 41,44, App B |
| PREREQUISITES | G20/G21 |
| FILES TO INSPECT | all artifacts |
| FILES TO CREATE/MODIFY | release_manifest + evidence index |
| INPUTS / OUTPUTS | Inputs: all artifacts. Outputs: release_manifest + evidence index. |
| INTERFACES / CONTRACTS | Canonical IDs/version fields and frozen upstream artifacts; exact subsystem interface is declared in code/config. |
| IMPLEMENTATION CONSTRAINTS | Missing evidence is explicit fallback, not fabricated. |
| TESTS | artifact/hash/gate audit |
| COMMANDS / RUN STEPS | run release checker |
| EXPECTED ARTIFACTS | v1.0 release package |
| ACCEPTANCE CRITERIA | all mandatory artifacts or documented fallback |
| RISKS | late missing gate |
| RECOVERY | downgrade scope honestly; preserve core rigor |
| WHAT MUST NOT CHANGE | No new methodology |
| GATE / FREEZE IMPACT | G22 |
| NEXT UNLOCKED DEPENDENCY | Submission |

# 23. Independent Verification Packets

| Review | Milestone | Locked sections | Audit files/components | Check for | Invoke |
| --- | --- | --- | --- | --- | --- |
| V01 | Contracts/G0-G1 | Sections 2-5,40 | contracts/, configs/, SOURCE_AUTHORITY | undefined units/timestamps, source conflicts, invented hardware facts | before any real data processing |
| V02 | Data/label/split G2-G5 | Sections 6-11 | datasets/, manifests/, labels, split audits | patient leakage, lead fallback, symbol coercion, 201/202 split | before preprocessing/model evidence |
| V03 | Preprocessing G6 | Section 8/11 | preprocessing/, causality tests | look-ahead, centered resampling, future gap interpolation, state mismatch | before baselines |
| V04 | MODEL_V1 G7-G8 | Sections 12-16 | features/, models/, training/, run manifests | held-out tuning, wrong seed selection, train-only fit violations | before calibration/test/FL |
| V05 | Central evaluation G10 | Sections 23-25 | calibration, internal/noise/external reports | test tuning, window bootstrap, false calibration domain | after E06 |
| V06 | Multimodal G9 | Sections 14-15 | quality/sync/fusion/episode/context experiment | learned-label creep, different thresholds between arms, episode double-count | after E08 |
| V07 | FedAvg/Non-IID G11-G12 | Sections 17-18 | client manifests, Flower app, logs | patient sharing, arbitrary rows, confounded budget | before FedProx |
| V08 | FedProx/SecAgg+ G13-G14 | Sections 19-20 | fedprox/privacy code/reports | unmatched variables, mu selection leakage, overbroad privacy claim | before release privacy/FL results |
| V09 | Wearable/API/UI G15-G19/G21 | Sections 21-22,27-28 | deployment, wearable, api, dashboard | hidden alternate pipeline, diagnostic wording, timestamp substitution | before final demo |
| V10 | Release G20-G22 | Sections 30-44 | lockfiles, scripts, reports, release manifest | manual steps, missing hashes, unsupported claims, dead critical-path code | final freeze |

Every review records severity (BLOCKER/MAJOR/MINOR), exact path/line or artifact ID, required correction, regression test and gate impact. The verification role does not redesign valid locked architecture.

# 24. Failure / Recovery / Fallback Strategy

| Failure | Trigger | Immediate containment | Recovery/version action | Evidence preserve | Fallback |
| --- | --- | --- | --- | --- | --- |
| Unexpected source annotation/channel | G3 validation fails | Stop mapping/split | fix loader or exclusion manifest; version if source facts change | raw + validation logs | Level 1 |
| Too few class-positive patients in split | split audit | Do not train | rerun predefined stratifier constraints before training; freeze once | candidate split stats | Level 1/2 |
| Causal resampler cannot pass chunk test | G6 | block all ML evidence | replace implementation; preserve spec output semantics | failing seeds/traces | Level 1 |
| CNN overfits/unstable | train-val divergence | keep classical baselines | simplify/regularize on validation only, version MODEL candidate | all learning curves | Level 1/2 |
| Calibration unstable due few patients | wide/erratic reliability | retain raw + source-calibrated fields | report limitation; do not claim wearable calibration | calibration outputs | Level 1 |
| INCART performance collapses | E06 | no retuning before primary report | report domain shift; exploratory adaptation separate future work | locked external predictions | Level 1 |
| PPG poor under motion | quality report | ECG-only context fallback | RECHECK/CONTEXT_UNAVAILABLE semantics | quality traces | Level 1 |
| Context increases alert chatter | E08 negative | do not tweak on test streams | check deterministic bug; otherwise report negative result | paired clean/degraded traces | Level 1 |
| FedAvg unstable | G11 | stop advanced FL | verify analytical aggregation, LR/state, IID first | round logs | Level 2 if unresolved |
| FedProx no gain | E13 | no rescue tuning on test | report null/negative; FedAvg remains reference | matched report | Level 1 |
| SecAgg+ integration fails | G14 | remove implemented privacy claim if deadline | debug current Flower reference; preserve threat model | failed protected logs | Level 3 |
| Gateway conversion unreliable | G15 | use PyTorch CPU gateway | benchmark research model directly | conversion comparison | Level 2 |
| Hardware delayed | no G16 data | continue replay/public evidence | minimal synchronized session when available; no fabricated hardware claim | fixtures/logs | Level 3 |
| Dashboard drift/diagnostic wording | G19 | block release | enum-driven UI + snapshot tests | failed UI states | Level 1 |
| Clean env fails | G20 | block release | fix path/dependency/script assumptions | fresh-run transcript | All levels |

## Fallback levels

Level 1 — Full: all G0–G22 mandatory scope.

Level 2 — Robust Reduced: preserve core rigor; cut UI polish, optional quantization, combined non-IID, ancillary figures/analyses. Keep MODEL_V1, internal/noise/external, RQ5 context experiment, FedAvg/FedProx core, SecAgg+ if passing, gateway, wearable, API/reproducibility.

Level 3 — Emergency: frozen target/split/causal preprocessing, classical baseline + CNN, internal + one external, deterministic quality gating + key context experiment, FedAvg IID + one non-IID, gateway replay, minimal synchronized wearable path, reproducible scripts. Remove FedProx/SecAgg+ if they cannot pass and remove their implemented claims.

# 25. “Do Not Start Yet” List

| Work | Blocked until | Reason |
| --- | --- | --- |
| CNN training | G4-G6 | label/split/preprocess changes would invalidate training |
| Calibration/test | G8 model lock | must calibrate a frozen model only |
| INCART performance exploration | G8 + primary external config frozen | avoid external-set model/lead/mapping selection |
| FedProx | G11 FedAvg PASS | otherwise algorithm comparison is uninterpretable |
| SecAgg+ | plain FedAvg aggregation correct | privacy cannot debug base aggregation |
| Final dashboard cosmetics | G18 API + G9 state semantics stable | avoid UI churn and unsafe wording |
| MCU inference optimization | G15 gateway characterization + exact board resources | optional scope; not evidence for mandatory system |
| Quantization | MODEL_V1 frozen + FP32 gateway benchmark | need reference predictions/resource need |
| Extra model families/datasets | defined RQ + change approval | complexity without evidence value |
| Large wearable collection | G1 contract + packet/sync pipeline verified + consent process | avoid unusable recordings |
| Final report numbers | evidence generated from locked runs | never manually reconstruct results |
| Any DP extension | all core gates passed | extension-only in v2.2 |

# 26. Demo Evolution

| Demo | Real components | Mock/fixture components | Allowed claim | Required evidence | Unlocks |
| --- | --- | --- | --- | --- | --- |
| Demo 0 — Day 1 | repo, schema validation, deterministic state/API smoke | synthetic fixture + mock probability | software skeleton only | day1_smoke.json | early integration confidence |
| Demo 1 — Causal ECG | real MIT-BIH loader/preprocess/windows | no final model required | data/causality pipeline works | G2-G6 reports | baseline/model work |
| Demo 2 — Centralized | real MODEL_V1 + calibration + internal replay | public data only | locked source-domain ECG research detector | G8/G10 artifacts | FL/gateway real integration |
| Demo 3 — Quality aware | real BIDMC context/episode manager; same MODEL_V1 | controlled perturbations | operational context robustness only | E07/E08 | multimodal RQ5 evidence |
| Demo 4 — Federated | real MODEL_V1/clients/FedAvg/FedProx; SecAgg+ if passed | synthetic research sites | controlled FL simulation | G11-G14 reports | final research story |
| Demo 5 — Wearable integration | real recorded AD8232/MAX30102 session→gateway→API→dashboard | none in replay path | domain-compatible end-to-end prototype; no clinical accuracy claim | G16/G18/G19/G21 | release |
| Final Demo | saved reproducible replay + optional live session + evidence registry | none required | all claims trace to artifacts and limitations | release manifest + clean run | submission/viva |

# 27. Final Release Sequence

Create a fresh clone/worktree at the release commit and recreate the Python environment from the committed lockfile.

Run full unit/integration/leakage/state/API test suite; save machine-readable test report.

Rebuild/verify public dataset manifests, hashes and license/source metadata without altering frozen versions.

Validate LABEL_SCHEMA_V1, symbol censuses, MITDB_SPLIT_V1 and all client manifests; save audit hashes.

Verify PREPROC_V1/GAP_POLICY_V1 causality reports and MODEL_V1 checksum/test vector.

Verify CAL_V1, internal, NSTDB and INCART final reports/prediction files.

Verify BIDMC engineering report, controlled quality-aware experiment and episode-state tests.

Verify FedAvg IID/non-IID and FedProx reports with frozen manifests/configs; verify SecAgg+ evidence or explicitly remove unsupported claim.

Run gateway benchmark and compare deploy artifact predictions to reference.

Replay a WEARABLE_V1 recorded session through the exact gateway/API/dashboard path and save logs/screenshots/video metadata.

Run clean CPU smoke command and save environment/hardware summary.

Generate experiment registry summary, final limitations, viva decision map and release_manifest.json with SHA-256 for every mandatory artifact.

Run coverage audit and Definition-of-Done checker; unresolved mandatory failures force a declared fallback level.

Tag release only after G22 PASS: v1.0-final (or equivalent).

# 28. Final Master Checklist

| Area | Release check |
| --- | --- |
| Scope/RQs | AAMI_SVF_WINDOW_V1 and non-diagnostic claim unchanged. |
| Contracts | hardware/data/label/API versions and hashes present. |
| Data | exact dataset releases/manifests; no PTB-XL core dependency. |
| Leads | MIT-BIH MLII; INCART II; exclusions pre-split. |
| Mapping | AAMI_SVF_MAP_V1 shared; unknown/paced excluded; symbol census saved. |
| Split | patient disjoint; 201/202 grouped; patient counts reported. |
| Causality | filter/resampler/gaps future-append and chunk tests pass. |
| Windows | 10s/5s, right-edge timestamp, no future sample. |
| Baselines | majority selected from train prevalence only. |
| MODEL_V1 | exact architecture/config/checkpoint/test-vector hash. |
| Calibration | MIT-BIH calibration only; threshold frozen; patient count/domain exposed. |
| Statistics | patient-cluster bootstrap 2000; no window-level CI; AUPRC recomputed pooled. |
| External | one primary INCART run before adaptation. |
| Multimodal | deterministic quality/context only; E08 paired operational experiment. |
| Alerts | K2/M2/cooldown30; episode metrics not window counts. |
| FL | 8 synthetic whole-patient sites; FedAvg before non-IID/FedProx. |
| FedProx | mu=0 equivalence; matched variables; label-skew validation tune only. |
| Privacy | SecAgg+ narrow claim or claim removed. |
| Edge | gateway benchmark measured; MCU claim absent unless separately evidenced. |
| Wearable | same pipeline; domain evidence only; consent/ethics satisfied. |
| XAI | IG exact baseline/steps/quadrature/case rule. |
| API/UI | safe enums/wording; model/preprocess/contract/alert/calibration IDs exposed. |
| Reproducibility | clean environment scripts + lock + run manifests. |
| Evidence | every claim traces to config/commit/run/artifact. |
| Gates | G0-G22 PASS or explicit fallback status. |
| Release | SHA-256 manifest + limitations + viva map + final tag. |

# 29. Coverage-Audit Result and Remaining Risks

Coverage result: the locked v2.2 requirements, E01–E16 experiments, G0–G22 gates, source verification items and Definition-of-Done clauses are all mapped to implementation, validation and evidence in Sections 3, 17, 18, 22 and 27. No mandatory v2.2 item is intentionally omitted from the Level-1 plan.

| Remaining risk | Why it remains | Mitigation in this plan | Decision trigger |
| --- | --- | --- | --- |
| Small patient counts | Cannot be fixed by more overlapping windows | patient counts beside windows; patient-cluster CIs; limited calibration claim | report uncertainty; no sample-size inflation |
| External domain shift | MIT-BIH/INCART/hardware differ | one locked external run + wearable domain report | report degradation; no retuning of primary external result |
| Hardware uncertainty | board/register/ADC details depend on actual build | Day-2 bench track + G1 block for wearable evidence | if unresolved, preserve raw counts and no unsupported conversion |
| SecAgg+ framework integration | current framework APIs can change | isolate privacy/FL modules; verify current docs/version; fallback removes claim | G14 fail near deadline -> Level 3 |
| Solo workload | Original schedule assumed three people | 16-week path, fixture progress, batch boundaries, fallback levels | miss latest-safe-start dates -> cut breadth |
| Wearable collection ethics/logistics | external approvals and participant availability | start approval/bench early; minimal safe sessions only | no collection until approved; public/replay work continues |
| Calibration instability | few calibration patients | record calibration n; source-domain-only wording | report limitation, do not imply clinical calibration |
| Operational context may not help | RQ5 could be negative | paired controlled design; report negative result honestly | no rule tuning on evaluation streams |

After G22, methodology changes stop. New findings become future work unless they reveal a correctness defect that invalidates existing evidence. The dominant risk then is implementation overload, not specification ambiguity.

# Day-1 Starter Block — Literal Execution Order

1) mkdir nhm && cd nhm && git init
2) mkdir -p contracts configs datasets manifests preprocessing features models fusion training federated privacy evaluation deployment api dashboard tests/fixtures experiments reports docs scripts release
3) python3.11 -m venv .venv && source .venv/bin/activate
4) python -m pip install --upgrade pip
5) python -m pip install pytest ruff pydantic pyyaml numpy
6) python --version > reports/day1_python_version.txt && python -m pip freeze > reports/day1_packages.txt
7) create: docs/SOURCE_AUTHORITY.md, docs/freeze_map.md, docs/do_not_start.md
8) create: configs/base.yaml, contracts/sample_schema_v1.json
9) create: tests/fixtures/session_v1.jsonl, tests/test_smoke.py, scripts/smoke_fixture.py
10) ruff check .
11) pytest -q
12) python scripts/smoke_fixture.py --input tests/fixtures/session_v1.jsonl --out reports/day1_smoke.json
13) python -m pip freeze > requirements.day1.lock.txt
14) git add . && git commit -m "bootstrap: authority, contracts, fixtures, smoke test"

End-of-Day-1 success: the repository is versioned, the authority hierarchy and frozen-scope controls exist, the canonical fixture passes its first contract test, the fixture-driven smoke path emits reports/day1_smoke.json, and a clean clone has enough documented information to reproduce that result. No model training, real split creation, federated experiment, SecAgg+, UI polishing or MCU optimization has begun.